## Slide 1: COURSE TITLE PROJECT ENGINEERING
Chapter 3 - (Week 6)
PROJECT PLANNING AND SCHEDULING
LECTURE – 6
Network Analysis: Introduction to Critical Path Method (CPM) .
Er. Ishwar Adhikari
Associate Professor
Kathmandu Engineering College, Nepal

## Slide 2: Learning Objective
The main objective of this lecture is to understand about :
Network analysis process of scheduling.
Introduction to Critical Path Method.
Critical Path
Terminologies of CPM
Calculation Procedure of CPM
Advantages and disadvantages of CPM.

## Slide 3: NETWORK ANALYSIS
For a project involving large number of activities, the project scheduling becomes very complex and the use of conventional method of scheduling like bar charts will not be effective.
The main aim of a project planning is to complete the project within stipulated time and doing the work in planned way [1]
One of the most popular technique of planning and scheduling the complex project is network analysis.
Complex projects, if not correctly scheduled, will most probably result in either under estimation or over estimation of the project implementation period, both of which will have serious consequences. [2]

## Slide 4: NETWORK ANALYSIS (Cont’d..)
For proper planning, scheduling and control of the activities of a project, given their inter-relationships and constraints on the availability of resources, network analysis have been found quiet useful. [3]
A network is the combination of different activities of the project. These activities are so connected that it defines the whole project. [4]
Most commonly used network analysis techniques are: Critical Path Method (CPM) and Program Evaluation and Review Technique (PERT).

## Slide 5: NETWORK ANALYSIS (Cont’d..)
Steps for Network analysis;
Whole Project is divided or broken down into a series of activities or work packages.
Activities are linked together according to their technological sequence of operation or logical relationship (preceding, succeeding and concurrent)
The time of completion or duration of each activity is estimated
The network diagram is drawn and from diagram the completion time of whole project is determined.

## Slide 6: CRITICAL PATH METHOD (CPM)
The technique of network based scheduling by critical path method(CPM) is used for planning and scheduling projects involving sequential operation. [5]
It is a deterministic approach and an activity oriented network diagram showing the interdependencies and relationship between the various activities.
CPM developed in the year 1957 by Morgan R. Walker of DU Pont and James E. Kelly of Remington Rand for preparing shutdown schedule of a chemical plant.

## Slide 7: CRITICAL PATH METHOD (CPM) TERMINOLOGIES
Activity(s):
An activity is a task or closely related group of tasks whose performance contributes to the completion of the overall project. [6]
Arrow in a network diagram represents activity and consume resources like manpower, material, money, time etc.
Examples: Excavation of foundation, construction of wall, electrical wiring etc.
A
B
C
Activity (i-j)
i
j
A is the predecessor of B
C is the Successor of B
1
2
3
4
A
B
1
A and B are Concurrent Activity

## Slide 8
Event/Node:
It is the point in time denoting completion of an activity and start of an activity. It does not consume resources.
CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
i
j
k
Event Event Event
Head/ Merge event
Tail/ Burst event
A
B
Dual role event

## Slide 9: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Duration (t)
Estimated time to perform a definite activity/task.
It is mentioned alongside with activity name.
The time unit for the project can be minutes, hours, work days, calendar days, weeks or months.
Activity Duration = Work Quantity/ Production rate
Excavation (5)
1
2

## Slide 10: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Dummy Activity
A dummy activity is an imaginary (hypothetical) activity included in a network.
Since it is not a real activity, it does not consume time, manpower, material and other resources.
It is included in a network to maintain the relationship between activities appropriately. It is represented by dotted arrow.
Excavation
2
3
5
Dummy activity
1
4
Supply of bricks
Soling
Brick Work

## Slide 11: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Grammatical purpose:
It is used to prevent two arrows having common beginning and end nodes for two or more activities.
For example, consider the arrows of activities A and B; both starts from node 1 and end at node 2.
Due to this an inconvenience results when the network is used for computation, i.e., uniqueness in the identification is lost. This inconvenience frequently leads to mistake. [7]

## Slide 12: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Logical purpose
Dummies are also used to give logical clear representation in a network having an activity common to two sets of operations running parallel to each other.
Here, Activity D cannot be started until Activity A is completed. The inter dependency or logical relation between two activities are clearly known.

## Slide 13: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Graphical Representation of activities and events
Activity on Arrow (AOA) system
In this system, an activity is represented by an arrow with circles at both ends drawn from left hand side to the right hand side.
The tail end of the arrow represents the start of an activity and head of arrow represents completion of activity.
Excavation
1
2

## Slide 14: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Activity on Node (AON) system
In this system, activities are represented by nodes or circles.
Arrow only shows the dependence of activities on each other.
No dummy activity is required to represent the inter dependency between succeeding and preceding activity.
It is also called precedence diagramming method (PDM)
ES
EF
LS
LF
ACTIVITY A
ES
EF
LS
LF
ACTIVITY B

## Slide 15: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Earliest start time (EST)
It is the earliest possible time that the activity can start.
Earliest finish time (EFT)
It is the earliest possible time for completion of an activity or operation without delaying the project completion time.
It can be computed by adding activity duration by EST.
EFT (i-j) = EST (i-j) + ti-j

## Slide 16: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Latest finish time (LFT)
It is the latest possible time that an activity can be finished based on the logic and duration identified on the network without extending the project duration. [8]
Latest start time (LST)
It is the latest possible time; an activity can be started without delaying the project.
LST (i-j) = LFT (i-j) - ti-j

## Slide 17: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Float / Slack
The free time available to the activity is called float or slack.
Total float (TF)
It is the extra time available when the start or finish of an activity can be delayed, without delaying the completion of the project. [5]
i
j
EST(i-j)
LST(i-j)
EFT(i-j)
LFT(i-j)
TF
TF
t(i-j)
EFT (i-j) = EST (i-j) + t (i-j)
LFT (i-j) = LST (i-j) + t(i-j)
LFT (i-j) – EFT (i-j) = LST (i-j) – EST (i-j)
TF = LFT (i-j) – EFT (i-j) OR LST (i-j) – EST (i-j)

## Slide 18: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Free float (FF)
It is the delay that can be permitted in an activity so that succeeding activities in the path are not affected. [2]
In other words, It is the extra time available when the activity is delayed without delaying the early start time of succeeding activity.
i
j
k
EST(i-j)
EFT(i-j)
EST(j-k)
FF
FF = EST (j-k) – EFT (i-j)

## Slide 19: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Independent float (IF1)
It is the spare time available for the activity, if preceding activity is started as late as possible and succeeding activities are finished as early as possible.
Interfering Float (IF2)
It is the name given to head event slack. It is the difference between total float and free float.
EFT (h-i) EST (j-k)
IF1= EST (j-k) – EFT (h-i)-ti-j
Also IF1= FF (i-j)-Tail event slack
IF2 = TF (i-j)- FF(i-j)

## Slide 20: CRITICAL PATH METHOD (CPM) TERMINOLOGIES (Cont’d…)
Critical Path
In a network diagram, the activities are represented by arrows and arrows flow from left to right.
In a network, there may be many paths starting from the initial event and leading to the last event.
If the duration of all the activities that lie on particular paths is added, it gives the duration of the path.
Each path in a network will have a different duration.

## Slide 21: Critical Path (Cont’d….)
Path | Description | Duration | Remarks
1 | 1 – 2 – 3 – 5 – 6 | 4+2+3+4 =13 days | 
2 | 1 – 2 – 4 – 5 – 6 | 4+5+6+4 =19 days | Longest/Critical path
3 | 1 – 2 – 4 – 6 | 4+5+1 =10 days | 

## Slide 22: Critical Path (Cont’d….)
The path that has the longest duration is called the critical path and the activities lying on the critical path are critical activities.
In a network diagram, the path along which the project takes the maximum time from start to finish is called critical path.
It is the longest path of the network and gives the total time taken to complete the project. Any delay along this path delays the project.

## Slide 23: CHARACTERISTICS OF CRITICAL PATH [2]
Critical path is the longest path (time wise) connecting the initial and final events.
Critical activity may run through dummy activity/activities also.
The number of activities lying on critical path may be less than the number of activities in other non critical activities.
It is possible that a network may have more than one critical path i.e. if two or more paths have the same time duration which is maximum, then all such paths will be critical paths.

## Slide 24: CHARACTERISTICS OF CRITICAL PATH (Cont’d…..)
Super critical activity
When the total float of the activity is negative, then this activity is called the super critical activity and demand very special attention and action. [1]
Critical activity
When the total float of the activity is zero, then this activity is called critical activity. Such activity permit no freedom of action and demand normal action.
Sub critical activity
When the total float is positive, then the activity is known as sub critical activity and permit freedom and demand normal attention.

## Slide 25: CALCULATION PROCEDURE OF CPM
Forward pass calculation
  In the forward pass calculation, all activities in the network are assumed to start as early as possible.
  The calculation begins from the left to the right side of the network.
  When two or more activities merge into a event, the largest value is taken as an earliest occurrence time of that event.
  Forward pass calculation gives the EST and EFT of each activity.

## Slide 26: CALCULATION PROCEDURE OF CPM (Cont’d….)
Backward pass calculation
In the backward pass calculation, all activities in the network are assumed to start as late as possible.
The calculation begins from the right to the left side of the network.
When two or more activity merges at a node, the smallest value is taken as a latest occurrence time of that event.
Backward pass calculation gives the LST and LFT of each activity.

## Slide 27: ERRORS IN NETWORK DIAGRAM
Activities should start from a single initial node and end on single final node.
2. There should not be a loop formation in the network.
A
B
F
C
E
D
1
2
3
4
5
1
2
3

## Slide 28: ERRORS IN NETWORK DIAGRAM (Cont’d..)
Two or more activities can start from a same common node but cannot end on a same common node.
There should not be an intersection between the activities.
1
2
1
2
3
4
5

## Slide 29: ERRORS IN NETWORK DIAGRAM (Cont’d..)
The number of arrows should not be more than the number of activities.
There should not be unnecessary dummy in the network diagram.
A
B
A
C
E
D
1
2
3
4
5
1
2
3
4
5

## Slide 30: ADVANTAGES AND DISADVANTAGES OF CPM
Advantages
Makes dependencies visible between the project activities.
Organizes large and complex projects, hence allowing a more systematic approach to project planning and scheduling.
Enables the calculation of float or slack of each activity.
Enables the Project Manager to optimize efficiency
Provides opportunities to respond to the negative risk going over schedule.
Encourages the Project Manager to reduce the project duration by optimizing the critical path

## Slide 31: ADVANTAGES AND DISADVANTAGES OF CPM (Cont’d..)
Disadvantages
CPM is not suitable for the project involving some uncertainties like research and development project.
Reduced Attention to High-Float Tasks: When using the critical path method, project managers focus on critical path tasks. For large and complex projects, there’ll be thousands of activities and dependency relationships. [9]
For large projects with thousands of activities, it may be difficult to print the project network diagram.
The Critical Path Method does not account for resource and resource allocation.

## Slide 32: REFERENCES
[1] Construction Management And Accounts: B.L.Gupta and Amit Gupta, Third Edition, Standard Publishers Distributors, New Delhi, India, 2000.
[2] Project Management: K. Nagarajan, New Age International (P) Ltd. Publishers, New Delhi, India, 2001.
[3] Projects; Planning, Analysis, Financing, Implementation and Review : Prasanna Chandra, Fifth Edition, Tata McGraw – Hill Publishing Company Limited, New Delhi, India, 2002.
[4] https://byjusexamprep.com/network-analysis-in-project-management
[5] Fundamentals of PERT/CPM and Project Management: S. K. Bhattacharjee, Second Edition, Khanna Publishers, New Delhi, India, 2002.

## Slide 33: REFERENCES (Cont’d…)
[6] Professional Construction management: Donald S. Barrie and Boyd C. Paulson Jr., Third Edition, McGraw Hill, Inc., 1992.
[7] Project Planning and Control with PERT and CPM: Dr. B.C. Punmia and K.K.Khandelwal, Third Edition, Laxmi Publications (P) Ltd, New Delhi, Inida, 1987.
[8] Managing the Construction Process, Estimating, Scheduling and Project Control : Second Edition, Frederick E. Gould, PE,CPC, Pearson Education, Inc., New Jersey, USA, 2002
[9] https://www.smartsheet.com/content/critical-path-advantages-disavantages